**Isicwangciso soLawulo lweNdalo kunye neNtlalo**

**I-PIMS 5686 Uphuhliso lwamakhonkco exabiso kwiimveliso ezithathwe kwimithombo yofuzo ngokuthobela iprotocol yaseNagoya ekufikeleleni kunye nokwabelana ngenzuzo kunye neqhinga lesizwe loqoqosho lwezityalo nezilwanyana.**

Uyilo lwezimvo 12 Dec 2024

# Isishwankathelo soLawulo

Kuya kongezwa

# Amanyathelo okunciphisa, ukubeka iliso nokuphunyezwa kwezicwangciso zokwenza

Eli candelo leSicwangciso soLawulo lokusiNgqongileyo kunye neNtlalo (ESMP) lichaza amaqhinga kunye neenkqubo eziyilelwe ukunciphisa, ukulawula, nokubeka iliso okunokubakho kokuchaphazeleka kokusingqongileyo nezentlalo ezinxulumene nemisebenzi yeprojekthi. Amanyathelo okunciphisa abonelela ngamanyathelo acacileyo okujongana nemingcipheko echongiweyo, ukuqinisekisa ukuba iziphumo ezibi ziyancitshiswa okanye ziyaphetshwa, kwaye iziphumo ezilungileyo ziyaphuculwa. Umgaqo-sikhokelo wokubeka iliso useka izalathisi, iishedyuli, kunye noxanduva lokulandelela impumelelo yala manyathelo, ukuqinisekisa ukuthotyelwa kwe-UNDP SES kunye nemimiselo yasekhaya. Isicwangciso sokusebenza sichaza iindima, amaxesha, izixhobo, kunye neendlela zokuphendula eziyimfuneko ukudibanisa la manyathelo kwimisebenzi yeprojekthi ngokufanelekileyo.

## Amanyathelo okunciphisa nokubekwa kweliso

**Isiphumo 1.1 Imiqobo ye-R&D edityaniswe nezifundo zeklinikhi kunye nokubhaliswa kweGinger yaseAfrika (Siphonochilus aethiopicus) njengomthombo webhayoloji ukunyanga ukudumba kunye nezifo ezingahambisaniyo nezoyiswayo ngendlela ethobelayo ye-ABS..**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Umngcipheko** | **Umlinganiselo wokunciphisa** | **Ingcaciso yomsebenzi** | **Amaqumrhu anoxanduva** | **Ingxelo** | **Uhlahlo lwabiwo-mali** | **Ukubaluleka** | **Umhla wokugqitywa** |
| **Umngcipheko 1- Iimpembelelo ezingalunganga kumaqela angahoywanga, kuquka nabasetyhini.** | Iintlanganiso zokubonisana ngesivumelwano se-ABS kufuneka ziqhutywe ngokwahlukeneyo nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni. | Amaqela agxininise nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni ukuze baqonde indima ekuvuneni nasekusetyenzweni kweGinger yaseAfrika, imidla yabo kunye nezinto abazikhethayo kwi-ABS. | RP | DFFE | Ngaphantsi kwePhulo 1.1 - uhlahlo lwabiwo-mali lweRP | Phezulu | Ukuphela kwexesha lokubonisana |
| **Umngcipheko 2- Umngcipheko wokungonelanga uthethathethwano nabachaphazelekayo** | Isicwangciso sokubonisana nabachaphazelekayo malunga nesivumelwano se-African Ginger ABS kwiphondo laseLimpopo, eMpumalanga naKwaZulu-Natal. | Imephu yabachaphazelekayo ichonga iqela ngalinye labathathi-nxaxheba ekufuneka kudityanwe nabo kunye nendima yalo ekuvuneni nasekusetyenzweni kweGinger yaseAfrika. Isicwangciso sokubonisana sibandakanya imihla yeentlanganiso, indawo, uluhlu lwabamenyiweyo kunye nee-ajenda. | RP | DFFE | Phantsi kweZiphumo 1.1 - uhlahlo lwabiwo-mali lweRP | Phezulu | Phambi kokuqalisa uthethwano noluntu |
| **Umngcipheko 3- Iinkxalabo okanye izikhalazo eziphakanyiswe ngabachaphazelekayo abangahoywanga kakuhle** | i-GRM yeprojekthi isebenze | I-GRM igqityiwe kwaye iyasebenza, kubandakanywa iifomu ezishicilelweyo zokungeniswa kwezikhalazo ezikhoyo kuluntu ngalunye. | DFFE | UNDP | Uhlahlo lwabiwo-mali lwe-SES | Phezulu | Ngaphambi kokwenza imisebenzi yePhulo 1.1 |
| I-GRM isasazwe kwabo bachaphazelekayo. | Abachaphazelekayo baqeqeshwa kwiGRM ngexesha leeseshoni zokubonisana nge-ABS kunye neefomu ezishicilelweyo zokungeniswa kwezikhalazo ezifumanekayo kwinqanaba loluntu. | RP | DFFE | Phantsi kweZiphumo 1.1 - uhlahlo lwabiwo-mali lweRP | Phezulu | Ukuphela kwexesha lokubonisana |
| **Umngcipheko we-4 - Ukungahambelani nemimiselo yokusingqongileyo kunye neengxabano zamazwe ngamazwe ezinokubakho kwimvelaphi yeGinger yaseAfrika engaqinisekanga** | Value proposition dossier kwijinja yaseAfrika ibandakanya isifundo sokuthotyelwa kwemimiselo yokusingqongileyo kunye namaxwebhu emvelaphi yeGinger yaseAfrika. | Uphononongo lokuthotyelwa kwemigaqo yokusingqongileyo kunye namaxwebhu emvelaphi yeGinger yase-Afrika ngexesha lokulungiswa kwedosi yesiphakamiso sexabiso. | RP | DFFE | Phantsi kweZiphumo 1.1 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ukugqitywa kokuphunyezwa komsebenzi. |
| **Umngcipheko 5 - Ukuphathwa kakubi kwelifa lenkcubeko ngenxa yokulima urhwebo** | **Iprothokholi ekhoyo yokurekhoda nokusebenzisa ulwazi lwemveli ukuhlaziya i-ABS kwiGinger yaseAfrika** | **Ukuphuhliswa kweprothokholi ekurekhodweni nasekusebenziseni ulwazi lwemveli lokuhlaziya i-ABS kwiGinger yase-Afrika, kulandela uMthetho woKhuselo, ukuPhakanyiswa, uPhuhliso kunye noLawulo loLwazi lweMveli, wama-2019 kunye neNEMBA (iSahluko sesi-6 kunye neMimiselo ehambelana nayo) kunye nokuqinisekisa ukukhuselwa ngokupheleleyo kwabo banolwazi lwemveli. . Ukongeza, i-IPP iya kubandakanya iProtocol yeFPIC** elandela yemigaqo yokuziphatha nokukhusela Ilifa leNkcubeko eliNgaphathekiyo ze-UNESCO | DFFE | UNDP | Phantsi kweZiphumo 1.1 - uhlahlo lwabiwo-mali lweRP | Phezulu | Phambi kokuqalisa uthethwano noluntu |

**Isiphumo 1.2 i-Bioproducting R&D eMntla Koloni iyaxhaswa, ikhulisa uqoqosho lwendawo yokuhlola izilwanyana nezityalo ezohlukeneyo kunye nokuseka ‘Iziko loPhuhliso lweBioproducts’ elibekwe ngobuchule.**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Umngcipheko** | **Umlinganiselo wokunciphisa** | **Ingcaciso yomsebenzi** | **Amaqumrhu anoxanduva** | **Ingxelo** | **Uhlahlo lwabiwo-mali** | **Ukubaluleka** | **Umhla wokugqitywa** |
| **Umngcipheko 1- Iimpembelelo ezingalunganga kumaqela angahoywanga, kuquka nabasetyhini.** | Iintlanganiso zokubonisana ngeDevil’s Claw Best Management Practices (BMP) kunye nenkcazo yeenkonzo zenkxaso kwiiprojekthi zoluntu kufuneka ziqhutywe ngokwahlukeneyo nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni. | Amaqela agxininise nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni ukuze baqonde indima yokuvuna nokulungiswa kweDevil’s Claw, izinto abazithandayo kunye nezinto abazikhethayo ukuze baxhase iiprojekthi zoluntu. | RP | DFFE | Ngaphantsi kwePhulo 1.2 - uhlahlo lwabiwo-mali lweRP | Phezulu | Ukuphela kwexesha lokubonisana |
| **Umngcipheko 2- Umngcipheko wokungonelanga uthethathethwano noluntu oluxhamlayo kwi-Hub** | Isicwangciso sokubonisana nabachaphazelekayo kudliwano-ndlebe lweDevil’s Claw malunga neenkonzo ezixhasayo kwiiprojekthi zoluntu. | Imephu yabachaphazelekayo ichonga iqela ngalinye labathathi-nxaxheba ekufuneka kudityanwe nabo kunye nendima yalo ekuvuneni nasekuqhubeni iDevil’s Claw. Isicwangciso sokubonisana sibandakanya imihla yeentlanganiso, indawo, uluhlu lwabamenyiweyo kunye nee-ajenda. | RP | DFFE | Phantsi kweZiphumo 1.2 - uhlahlo lwabiwo-mali lweRP | Phezulu | Phambi kokuqalisa uthethwano noluntu |
| **Umngcipheko 3- Iinkxalabo okanye izikhalazo eziphakanyiswe ngabathathi-nxaxheba abafumana inxaxheba kwikhwelo lesindululo esingaqwalaselwanga kakuhle.** | I-GRM yeprojekthi iyasebenza  | I-GRM igqityiwe kwaye iyasebenza, kubandakanywa iifomu ezishicilelweyo zokungeniswa kwezikhalazo ezikhoyo kuluntu ngalunye. | DFFE | UNDP | Uhlahlo lwabiwo mali yeSES | Phezulu | Ngaphambi kokwenza imisebenzi yePhulo 1.1 |
| I-GRM isasazwe kwabachaphazelekayo kunye naBasebenzi beZiko. | Abachaphazelekayo baqeqeshwa kwi-GRM ngexesha leeseshoni zokubonisana nabasebenzi ngexesha leeseshoni zoqeqesho lwe-Hub kunye neefomu eziprintiweyo zokungeniswa kwezikhalazo ezikhoyo kwinqanaba loluntu. | RP | DFFE | Phantsi kweZiphumo 1.2 - uhlahlo lwabiwo-mali lweRP | Phezulu | Ukuphela kwexesha lokubonisana. |
| **Umngcipheko 4-Ukungahambelani nemigaqo yokusingqongileyo kunye nokungquzulana okunokubakho kwamazwe ngamazwe malunga nemvelaphi kaMtyholi engaqinisekanga.** | Isicwangciso sophando seminyaka emi-3 siquka isifundo sokuthotyelwa kwemigaqo yokusingqongileyo kunye namaxwebhu iDevil’s Claw. | Uphononongo lokuthotyelwa kwemigaqo yokusingqongileyo kunye namaxwebhu emvelaphi kaDevil's Claw ukuze kucaciswe isicwangciso sophando seminyaka emi-3. | RP | DFFE | Phantsi kweZiphumo 1.2 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ukugqitywa kophuhliso lwesicwangciso sophando seminyaka emi-3. |
| **Umngcipheko 5 - Ukuphathwa kakubi kwelifa lenkcubeko ngenxa yokulima urhwebo** | **Iprothokholi ekhoyo yokurekhoda nokusebenzisa ulwazi lwemveli kwisicwangciso sophando iDevil’s Claw.** | **Ukuphuhliswa kweprothokholi ekurekhodweni nasekusetyenzisweni kolwazi lwemveli lweDevil’s Claw, kulandela uMthetho woKhuseleko, ukuKhuthazwa, uPhuhliso noLawulo loLwazi lweMveli, wama-2019 kunye neNEMBA (iSahluko sesi-6 kunye neMimiselo ehambelana nayo) kunye nokuqinisekisa ukukhuselwa ngokupheleleyo kwabo banolwazi lwemveli. Ukongeza, i-IPP iya kubandakanya iProtocol yeFPIC** elandela yemigaqo yokuziphatha nokukhusela Ilifa leNkcubeko eliNgaphathekiyo ze-UNESCO | DFFE | UNDP | Phantsi kweZiphumo 1.1 - uhlahlo lwabiwo-mali lweRP | Phezulu | Ukugqitywa kophuhliso lwesicwangciso sophando seminyaka emi-3. |
| **Umngcipheko wesi-6 -Abantu baseSan banokuchatshazelwa kakubi kukuphunyezwa kwemisebenzi, kubandakanywa iMvume yoLwazi yaNgaPhambili yaSimahla (FPIC) engafunyanwanga ngokufanelekileyo.** | ISicwangciso saBantu beMveli (Indigenous Peoples Plan) (IPP) sihlaziywe ukuze siquke iProtocol yeFPIC ukwenzela ukubonisana namaqela amaSan kwiindawo ekujoliswe kuzo. | n/a | UNDP | n/a | Uhlahlo lwabiwo mali lweSES | Phezulu | Phambi kwesicwangciso sophando seminyaka emi-3 kunye nokuqukunjelwa kwee-BMPs. |
| Ukuphunyezwa kwamanyathelo achazwe kwi-IPP | n/a | RP | DFFE | Phantsi kweZiphumo 1.2 - uhlahlo lwabiwo-mali lweRP | Phakathi | Phambi kwesicwangciso sophando seminyaka emi-3 kunye nokuqukunjelwa kwee-BMPs. |
| **Umngcipheko 7 – Ukungahlonitshwa okunokwenzeka kwabasebenzi kunye neemeko zokusebenza** | I-ARC ibonisa indlela ehlangabezana ngayo neemfuno zeemeko zelizwe lomsebenzi kunye neemeko zokusebenza kwaye ibonelele ngamanyathelo okhuseleko ngokwemisebenzi yokulima kwiingxelo zabo zekota. | I-ARC inikezela ngamaxwebhu kwi-RP (izivumelwano zabasebenzi, iinkqubo zokhuseleko, ubungqina bezinto ezikhuselekileyo njl.) ukubonisa indlela abaza kuhlangabezana ngayo neemfuno zelizwe lomsebenzi kunye neemeko zokusebenza kunye nokubonelela ngamanyathelo okhuseleko kwimisebenzi ye-Hub. Uhlaziyo lurekhodwa kwiingxelo ze-trimestral kwi-RP. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Kufuneka igqitywe phambi kokusekwa kweHub. Ixesha elihlaziyiweyo: ingxelo yetrimestra elandelayo kwi-DFFE.  |
| **Umngcipheko wesi-8 - Ungcoliseko olunokubakho lwe-ecosystem kunye nokusetyenziswa kwamandla ekulinyweni kweDevil's Claw.** | Uluntu luqeqeshelwa izindululo malunga nosetyenziso oluzinzileyo kunye nemilinganiselo yokunciphisa ukusetyenziswa kwezitshabalalisi, izichumisi kunye nokusetyenziswa kwamandla okubandakanyiweyo kwii-BMPs. | Zibandakanye ezi mfuno kwikharityhulam kwaye uququzelele uqeqesho noluntu. | RP | DFFE | Phantsi kweZiphumo 1.2 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokuba iinkonzo zenkxaso zinikezelwe kwiiprojekthi zoluntu. |
| Ii-BMP zokulima nokucwangciswa kokuvuna kunye nenkxaso yokulungiswa kwemveliso yezolimo kunye nokulawulwa komgangatho wokufakwa kwemveliso kubandakanya iingcebiso malunga nosetyenziso oluzinzileyo kunye namanyathelo okunciphisa ukusetyenziswa kweyeza zinambuzane, izichumisi kunye nokusetyenziswa kwamandla. | Ukuqesha umcebisi ukuphuhlisa ezi zixhobo. | RP | DFFE | Phantsi kweZiphumo 1.2 - uhlahlo lwabiwo-mali lweRP | Phakathi | Iinguqulelo zokugqibela ze-BMPs. |
| I-ARC ibonisa indlela ezisebenzisa ngayo izitshabalalisi, izichumisi kunye nokusetyenziswa kwamandla kwiziko le-Hub kwiingxelo zabo zekota. | I-ARC ibonelela ngamaxwebhu kwi-RP ukubonisa indlela indawo ezisebenzisa ngayo izitshabalalisi, izichumisi kunye nokusetyenziswa kwamandla. Uhlaziyo lurekhodwa kwiingxelo zekota ukuya kwiRP. | RP | DFFE | Phantsi kweZiphumo 1.2 - uhlahlo lwabiwo-mali lweRP | Phakathi | Kufuneka igqitywe phambi kokusekwa kweHub. Ixesha elihlaziyiweyo: ingxelo yetrimestra elandelayo kwi-DFFE.  |

**Isiphumo 2.1 Ukuphunyezwa kwe-Pelargonium Biodiversity Management Plan (BMP) ixhaswa ngentsebenziswano esondeleyo phakathi kweQela eliSebenzayo lePelargonium, amashishini oluntu kunye nabachaphazelekayo kwiCSO.**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Umngcipheko** | **Umlinganiselo wokunciphisa** | **Ingcaciso yomsebenzi** | **Amaqumrhu anoxanduva** | **Ingxelo** | **Uhlahlo lwabiwo-mali** | **Ukubaluleka** | **Umhla wokugqitywa** |
| **Umngcipheko 1- Iimpembelelo ezilinganayo ze-Pelargonium Biodiversity Management Plan (BMP), i-ABS kunye nokufikelela kuqeqesho kumaqela angakhathalelwanga, kuquka nabasetyhini.** | Iintlanganiso zothethwano ngePelargonium Best Management Plan (BMP) kunye ne-ABS kufuneka ziqhutywe ngokwahlukeneyo nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni. | Focus groups with women, youth and other vulnerable people to understand role in Pelargonium harvesting and processing, their interests and preferences for ABS.  | RP | DFFE | Under Output 2.1 – RP budget | Phezulu | End of consultation period |
| Abasetyhini, ulutsha kunye nabanye abantu abasesichengeni baqeqeshelwa ukuvuna endle okuzinzileyo. | Bandakanya izabelo zabathathi-nxaxheba (umzekelo, i-50% yabasetyhini) kuqeqesho. | RP | DFFE | Phantsi kweZiphumo ze-2.1 - ibhajethi yeRP | Phezulu | Phambi koqeqesho kwizenzo ezizinzileyo |
| **Umngcipheko 2- Ukungabikho kothethathethwano noluntu** | Ukwenziwa kweemephu kunye nesicwangciso sokubonisana nabachaphazelekayo ukulungiselela uthethwano lweSicwangciso esiLawulayo sePelargonium. | Ukwenziwa kweemephu kwabachaphazelekayo kuchonga iqela ngalinye labathathi-nxaxheba ekufuneka kudityanwe nabo kunye nendima yalo ekuvuneni nasekusetyenzweni kwePelargonium. Isicwangciso sokubonisana sibandakanya imihla yeentlanganiso, indawo, uluhlu lwabamenyiweyo kunye nee-ajenda. | RP | DFFE | Phantsi kweZiphumo 2.1 - uhlahlo lwabiwo-mali lweRP | Phezulu | Phambi kokuqalisa uthethwano noluntu |
| **Umngcipheko 3- Iinkxalabo okanye izikhalazo eziphakanyiswe luluntu oluzibandakanya ekuvuneni ipelargonium** | I-GRM ye projekthi iyasebenza  | I-GRM igqityiwe kwaye iyasebenza, kubandakanywa iifomu ezishicilelweyo zokungeniswa kwezikhalazo ezikhoyo kuluntu ngalunye. | DFFE | UNDP | SES budget | Phezulu | Prior to conducting Output 1.2 activities |
| I-GRM isasazwe kwabo bachaphazelekayo | Abathathi-nxaxheba abachongiweyo kwimephu yabachaphazelekayo baqeqeshwa kwi-GRM ngexesha leeseshoni zothethwano kunye neefomu ezishicilelweyo zokungeniswa kwezikhalazo ezikhoyo kwinqanaba loluntu. | RP | DFFE | Phantsi kweZiphumo 1.2 - uhlahlo lwabiwo-mali lweRP | Phezulu | Ukuphela kwexesha lokubonisana. |
| **Umngcipheko 4 - Ukuphathwa kakubi kwelifa lenkcubeko yepelargonium** | **Iprothokholi ekhoyo yokurekhoda nokusebenzisa ulwazi lwemveli lwePelargonium kwi-BMP.** | **Ukuphuhliswa kweprothokholi ekurekhodweni nasekusetyenzisweni kolwazi lwemveli lwePelargonium, kulandela uMthetho woKhuselo, ukuPhakanyiswa, uPhuhliso kunye noLawulo loLwazi lweMveli, wama-2019 kunye neNEMBA (iSahluko sesi-6 kunye neMimiselo ehambelana nayo) kunye nokuqinisekisa ukukhuselwa ngokupheleleyo kwabo banolwazi lwemveli. Ukongeza, i-IPP iya kubandakanya iProtocol yeFPIC** elandela yemigaqo yokuziphatha nokukhusela Ilifa leNkcubeko eliNgaphathekiyo ze-UNESCO**.** | DFFE | UNDP | Phantsi kweZiphumo 1.2 - uhlahlo lwabiwo-mali lweRP | Phezulu | Phambi kokuqukunjelwa kweBMP kunye nokuvunywa nguMphathiswa ukuze uluntu luhlomle. |

**Isiphumo 2.2 Uphuhliso lwendawo yokuvuna iAloe ferox, ukusetyenzwa kunye nokurhweba eMpuma Koloni ngenjongo yokukhuthaza ukwabelana ngenzuzo ezinzileyo nelinganayo kuwo onke amakhonkco exabiso.**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Umngcipheko** | **Umlinganiselo wokunciphisa** | **Ingcaciso yomsebenzi** | **Amaqumrhu anoxanduva** | **Ingxelo** | **Uhlahlo lwabiwo-mali** | **Ukubaluleka** | **Umhla wokugqitywa** |
| **Umngcipheko 1- Iimpembelelo ezingalunganga kumaqela angahoywanga, kubandakanywa abasetyhini ngaphakathi kweTyefu** | Iintlanganiso zokubonisana malunga nokuvunwa kweAloe ferox, ukusetyenzwa kunye nendawo yokurhweba kufuneka ziqhutywe ngokwahlukeneyo nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni. | Amaqela agxininise nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni ukuze baqonde indima ekuvuneni nokusetyenzwa kweAloe Ferox, izinto abazithandayo kunye nezinto abazikhethayo kwindawo. | RP | DFFE | Phantsi kweZiphumo ze-2.1 - ibhajethi yeRP | Phezulu | Ukuphela kwexesha lokubonisana |
| Abasetyhini, ulutsha kunye nabanye abantu abasesichengeni abaqeqeshwe kulawulo lweProjekthi yoLawulo lweShishini lokuVuna okuZinzileyo | Bandakanya izabelo zabathathi-nxaxheba (umzekelo, i-50% yabasetyhini) kuqeqesho. | RP | DFFE | Ngaphantsi kweZiphumo ze-2.2 - ibhajethi yeRP | Phezulu | Phambi koqeqesho kwizenzo ezizinzileyo |
| Abasetyhini, ulutsha kunye nabanye abantu abasesichengeni baqeshwa njengabasebenzi kwindawo yokuvuna nakwiplanti yokulungisa nokupakisha.  | Bandakanya izabelo zabasetyhini, ulutsha kunye nabanye abantu abasesichengeni njengabasebenzi bokuvuna nakwiplanti yokulungisa nokupakisha. | RP | DFFE | Phantsi kweZiphumo ze-2.1 - ibhajethi yeRP | Phezulu | Ngaphambi kokuqala kokuvuna kunye nokusebenza kwesityalo. |
| **Umngcipheko 2- Umngcipheko wokungonelanga uthethathethwano noluntu lwaseTyefu** | Ukwenziwa kweemephu kunye nesicwangciso sokubonisana nabachaphazelekayo ukulungiselela ukubandakanya uluntu kwimisebenzi yekhonkco lexabiso leAloe Ferox. | Ukwenziwa kweemephu kwabachaphazelekayo kuchonga iqela ngalinye labachaphazelekayo ekufanele kudityanwe nalo kunye nendima yalo ekuvuneni, ukusetyenzwa nokupakishwa kweAloe Ferox. Isicwangciso sokubonisana sibandakanya imihla yeentlanganiso, indawo, uluhlu lwabamenyiweyo kunye nee-ajenda. | RP | DFFE | Phantsi kweZiphumo 2.1 - uhlahlo lwabiwo-mali lweRP | Phezulu | Phambi kokuqalisa uthethwano noluntu |
| **Umngcipheko 3- Iinkxalabo okanye izikhalazo eziphakanyiswe ngamalungu oluntu lwaseTyefu ekuyileni nasekuphunyezweni kwemisebenzi** | Iprojekthi yeGRM iyasebenza | I-GRM igqityiwe kwaye iyasebenza, kubandakanywa iifomu ezishicilelweyo zokungeniswa kwezikhalazo ezikhoyo kuluntu ngalunye. | DFFE | UNDP | Uhlahlo lwabiwo-mali lwe-SES | Phezulu | Phambi kokwenza imisebenzi yePhulo 1.2 |
| I-GRM isasazwe kwabachaphazelekayo kunye |  | RP | DFFE | Phantsi kweZiphumo 2.2 - uhlahlo lwabiwo-mali lweRP | Phezulu | Ukuphela kwexesha lokubonisana. |
|  | Umsebenzisi wokuvuna kunye nokusebenzisa isicwangciso ubonisa indlela esihlangabezana ngayo neemfuno zeemeko zabasebenzi kunye neemeko zokusebenza kunye nokubonelela ngemilinganiselo yokhuseleko ngokwemisebenzi yokulima kwiingxelo zabo zetrimestra. | Abathathi-nxaxheba abachongiweyo kwimephu yabachaphazelekayo baqeqeshwa kwi-GRM ngexesha leeseshoni zothethwano kunye neefomu ezishicilelweyo zokungeniswa kwezikhalazo ezikhoyo kwinqanaba loluntu. | RP | DFFE | Phantsi kweZiphumo 2.2 - uhlahlo lwabiwo-mali lweRP | Phakathi | Phambi kokuqalisa ukuvuna naphambi kokuqalisa ukusebenza kwesityalo. |
| Iikontraki ezingaphantsi kwazo zibonisa indlela ezihlangabezana ngayo neemfuno zelizwe labasebenzi kunye neemeko zokusebenza kwaye zibonelela ngamanyathelo okhuseleko. | I-Operator inikezela ngamaxwebhu kwi-RP (izivumelwano zabasebenzi, iinkqubo zokhuseleko, ubungqina bezinto ezikhuselekileyo njl.) ukubonisa indlela abaza kuhlangabezana ngayo neemfuno zelizwe kunye neemeko zokusebenza kunye nokubonelela ngamanyathelo okhuseleko kwimisebenzi ye-Hub. Uhlaziyo lurekhodwa kwiingxelo ze-trimestral kwi-RP. | RP | DFFE | Phantsi kweZiphumo 2.2 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokuqalisa inkqubo yokuthenga. |
| **Umngcipheko 4 – Ukungahlonitshwa okunokwenzeka kwabasebenzi kunye neemeko zokusebenza** | Uluntu luqeqeshwe kwiingcebiso malunga nosetyenziso oluzinzileyo kunye namanyathelo okunciphisa ukusetyenziswa kwezitshabalalisi, izichumisi kunye nokusetyenziswa kwamandla njengenxalenye yolawulo lweProjekthi yoLawulo lweShishini loVuno oluZinzileyo. | Bandakanya ukuthotyelwa kweemfuneko zeemeko zomsebenzi kazwelonke kunye neemeko zokusebenza kwinkqubo yokuthengwa kwezixhobo zabasebenzi kunye nezixhobo zeplanti. | RP | DFFE | Phantsi kweZiphumo 2.2 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokuba iinkonzo zenkxaso zinikezelwe kwiiprojekthi zoluntu. |
| Ukucubungula kunye nokupakisha umqhubi wezityalo ubonisa indlela esebenzisa ngayo i-pesticides, izichumisi kunye nokusetyenziswa kwamandla kwiziko le-Hub kwiingxelo zabo ze-trimester. | Zibandakanye ezi mfuno kwikharityhulam kwaye uququzelele uqeqesho noluntu. | RP | DFFE | Phantsi kweZiphumo 2.2 - uhlahlo lwabiwo-mali lweRP | Phakathi | Phambi kokuba uqalise ukusebenzisa umzi-mveliso, yonke ikota yenza ingxelo kwi-DFFE emva koko. |

**Iziphumo 2.3 Amashishini asekwe eluntwini kulimo lweHoneybush ayaxhaswa, eqinisekisa ulondolozo kunye neziphumo zokwabelana ngenzuzo ngokulinganayo kulo lonke elaseCyclopia spp. imbonakalo yomhlaba kwiNgingqi yaseKapa.**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Umngcipheko** | **Umlinganiselo wokunciphisa** | **Ingcaciso yomsebenzi** | **Amaqumrhu anoxanduva** | **Ingxelo** | **Uhlahlo lwabiwo-mali** | **Ukubaluleka** | **Umhla wokugqitywa** |
| **Umngcipheko 1- Iimpembelelo ezingalunganga kumaqela angahoywanga, kuquka nabasetyhini** | Izicelo ezifakwe ngabasetyhini kunye namashishini oluntu abamnyama abekwe phambili. | Kusetyenziswe indlela yokuhlela izindululo ukuxhasa ngokukhethekileyo iiprojekthi ezinceda imibutho yasekuhlaleni ekhokelwa ngabasetyhini kunye nabamnyama. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokusungulwa kwefowuni yesibini yesindululo |
| **Umngcipheko 2- Umngcipheko wokungonelanga kwamashishini akhokelwa luluntu** | Iinkalo zenkxaso yezibonelelo ezincinci ezichazwe ngokubonisana noluntu ekujoliswe kulo. |  Bandakanya iikowuta zabaxhamli umz. I-50% yabasetyhini abaqeqeshelwe ukuvuna endle okuzinzileyo. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokusungulwa kwefowuni yesibini yesindululo |
| Ii-NGOs kunye namashishini akhokelwa luluntu kunye namaqela okuvuna endle ayalazi ikhwelo lesindululo, kuqwalaselwe ngokukodwa abafazi kunye namashishini abamnyama. | Kuqhutywe uthethwano noluntu ukuze kuchazwe iifestile zenkxaso ngengxowa-mali yenkxaso-mali encinci ehlangabezana neemfuno zoluntu. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokuvalwa komhla wokuvalwa kwesicelo sokucela isindululo. |
| **Umngcipheko 3- Iinkxalabo okanye izikhalazo eziphakanyiswe ngabathathi-nxaxheba abafumana inxaxheba kwikhwelo lesindululo esingaqwalaselwanga kakuhle.** | Ababoneleli ngenkonzo baqeqeshelwe ukuphunyezwa kweGRM kunye nendima yabo. | Ukuququzelela iintlanganiso zokwazisa kunye nezixhobo zonxibelelwano ukuze kubhengezwe ikhwelo lesibini leziphakamiso kumashishini akhokelwa luluntu, kugxilwe ngokukhethekileyo kwabasetyhini kunye namashishini aphantsi kwabantu abamnyama. | UNDP | n/a | Uhlahlo lwabiwo-mali lwe-SES | Phezulu | Ngaphambi kokuba kuqaliswe umnxeba wesibini weziphakamiso. |
| Iphulo lokwazisa uluntu ngeprojekthi yeGRM kuluntu ekujoliswe kulo kunye nabo banokuba ngabaxhamli. | Uqeqesho lwababoneleli-nkonzo malunga nokuphunyezwa kweGRM kunye nendima yabo. | RP | UNDP | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phezulu | Ngaphambi kokuba kuqaliswe umnxeba wesibini weziphakamiso. |
| **Umngcipheko 4 – Ukulinywa korhwebo lweentlobo ezikhokelela kwiimpembelelo ezingalunganga kubomi bendalo bendalo** | Uluntu luqeqeshelwa ukuvunwa okuzinzileyo kwe-honeybush. | Uthethwano noluntu lubandakanya imodyuli emalunga ne-GRM kunye nendlela abahlali abanokufikelela ngayo kuyo kunye neefomu zokungeniswa kwezikhalazo eziprintiweyo ezifumanekayo kwinqanaba loluntu. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ukuqala kwekhontrakthi yesibonelelo. |
| Uvavanyo lwezibonelelo, isicwangciso sokubeka iliso, iziKhokelo zokuVuna okuZinzileyo, iSicwangciso soLawulo lweBiodiversity siphuhliselwa iHoneybush. | Ququzelela uqeqesho kunye namashishini akhokelwa luluntu abafumana inkxaso-mali encinci. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokukhutshwa kwekhontrakthi yesibonelelo. |
| IQela leNgcebiso yezobuGcisa be-honeybush (TAG) limiselwe ukujonga ukuphunyezwa kwenkxaso-mali encinci ngokweZikhokelo zokuVuna okuZinzileyo, iSicwangciso soLawulo lweZilwanyana zeNdalo. | Ukuqesha umcebisi ukuphuhlisa ezi zixhobo. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokuvalwa komhla wokuvalwa kwesicelo sokucela isindululo. |
| Ukukhusela ukujongwa kwezindululo zegranti ngokuchasene nemingcipheko echongiweyo phantsi kwemveliso 2.3 phambi kokuzinikela ngemali. | Lungiselela iiToRs, chonga amalungu, uchaze inkqubo yomsebenzi kwaye umisele iTAG. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokukhutshwa kwekhontrakthi yesibonelelo. |
| **Umngcipheko wesi-5-Urhwebo kunye nokuvuna endle okukhokelela ekunciphiseni inani labantu bezilwanyana ezisengozini kunye nokwanda korhwebo olungekho mthethweni.** | Uluntu luqeqeshelwa ukuvunwa okuzinzileyo kwe-honeybush. | I-RP iqulunqa uluhlu lokukhangela olusekelwe kwimingcipheko echongiweyo kwiSiphumo 2.3 ukuqinisekisa ukuba i-ikhosistim yendalo ichongiwe kwaye akukho nanye imisebenzi ecetywayo ngumfaki-sicelo eya kukhokelela kwimpembelelo embi. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ukuqala kwekhontrakthi yesibonelelo. |
| Uvavanyo lwezibonelelo, isicwangciso sokubeka iliso, iziKhokelo zokuVuna okuZinzileyo, iSicwangciso soLawulo lweBiodiversity siphuhliselwa iHoneybush. | Ququzelela uqeqesho kunye namashishini akhokelwa luluntu afumana inkxaso-mali encinci | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokukhutshwa kwekhontrakthi yesibonelelo. |
| Imibutho yasekuhlaleni ibonisa indlela imisebenzi ecetywayo elandela ngayo imigaqo yokuvuna ezinzileyo. | Ukuqesha umcebisi ukuphuhlisa ezi zixhobo. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokusungulwa kwefowuni yesibini yesindululo |
| Ukukhusela ukujongwa kwezindululo zegranti ngokuchasene nemingcipheko echongiweyo phantsi kwemveliso 2.3 phambi kokuzinikela ngemali. | I-RP ibandakanya icandelo leemfuno okanye itemplate yesindululo efuna abafaki-zicelo babonise ukuba imisebenzi ecetywayo ilandela njani imigaqo yokuvuna ezinzileyo. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokukhutshwa kwekhontrakthi yesibonelelo. |
| **Umngcipheko 6 - Ukuphathwa kakubi kwelifa lenkcubeko ngenxa yokulima urhwebo** | Iprothokholi ekhoyo yokurekhoda nokusebenzisa ulwazi lwemveli kwiiprojekthi ezixhaswa ngemali yinkxaso-mali encinci yophuhliso lwexabiso le-honeybush. | I-RP iqulunqa uluhlu lokukhangela ukuqinisekisa ukuba akukho nanye imisebenzi ecetywayo ngumfaki-sicelo eya kukhokelela ekuncitshisweni kwezityalo. | DFFE | UNDP | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phezulu | Ngaphambi kokukhutshwa kwekhontrakthi yesibonelelo. |
| **Umngcipheko wesi-7 - Abantu abangamaKhoi banokuchatshazelwa kakubi kukuphunyezwa kwemisebenzi, kubandakanywa iMvume yoLwazi yaNgaPhambili yaSimahla (FPIC) engafunyanwanga kakuhle.** | ISicwangciso saBantu beMveli (Indigenous Peoples Plan) (IPP) sihlaziywe ukuze siquke iProtocol yeFPIC ukwenzela ukubonisana namaqela amaKhoi kuluntu kwiindawo ekujoliswe kuzo. | Ukuphuhliswa kweprothokholi ekurekhodweni nasekusetyenzisweni kolwazi lwemveli lwe-Honeybush, kulandela uMthetho woKhuselo, ukuPhakanyiswa, uPhuhliso kunye noLawulo loLwazi lweMveli, wama-2019 kunye neNEMBA (iSahluko sesi-6 kunye neMimiselo ehambelana nayo) kunye nokuqinisekisa ukhuseleko olupheleleyo lwabanini-lwazi lwemveli. Ukongeza, i-IPP iya kubandakanya iProtocol yeFPIC elandela yemigaqo yokuziphatha nokukhusela Ilifa leNkcubeko eliNgaphathekiyo ze-UNESCO. | UNDP | n/a | Uhlahlo lwabiwo-mali lwe-SES | Phezulu | Ngaphambi kokuba kuqaliswe umnxeba wesibini weziphakamiso. |
|  | n / A | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokukhutshwa kwekhontrakthi yesibonelelo. |
| **Umngcipheko 8 – Ungcoliseko olunokubakho lwe-ecosystem kunye nokusetyenziswa kwamandla ekulimeni nasekuqhubeni imisebenzi** |  | n / A | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ukuqala kwekhontrakthi yesibonelelo. |
| Ukuphunyezwa kwamanyathelo achazwe kwi-IPP | Ququzelela uqeqesho kunye namashishini akhokelwa luluntu afumana inkxaso-mali encinci | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokukhutshwa kwekhontrakthi yesibonelelo. |
| Uluntu luqeqeshelwa ukuvunwa okuzinzileyo kwe-honeybush. | Ukuqesha umcebisi ukuphuhlisa ezi zixhobo. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokusungulwa kwefowuni yesibini yesindululo |
| Uvavanyo lwezibonelelo, isicwangciso sokubeka iliso, iziKhokelo zokuVuna okuZinzileyo, iSicwangciso soLawulo lweBiodiversity siphuhliselwa iHoneybush. | I-RP ibandakanya icandelo leemfuno okanye itemplate yesindululo efuna abafaki-zicelo babonise indlela abaza kusebenzisa ngayo izibulali-zinambuzane, izichumisi kunye namandla. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokukhutshwa kwekhontrakthi yesibonelelo. |
| **Umngcipheko 9 – Ukungahlonitshwa okunokwenzeka kwabasebenzi kunye neemeko zokusebenza yimibutho efumana izibonelelo** | Imibutho yasekuhlaleni ibonisa indlela abaza kusebenzisa ngayo izitshabalalisi, izichumisi kunye nokusetyenziswa kwamandla kwisicelo sabo sokucela isiphakamiso. | I-RP iphuhlisa uluhlu lokutshekisha olusekwe kwimingcipheko echongiweyo kwiSiphumo 2.3 ukuqinisekisa ukuba akukho nanye imisebenzi ecetywayo ngumfaki-sicelo eya kukhokelela kungcoliseko lwe-ecosystem kunye nokusetyenziswa kwamandla aphezulu. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokusungulwa kwefowuni yesibini yesindululo |
| I-RP ibandakanya icandelo kwiimfuno okanye i-proposal template efuna abafaki-zicelo babonise indlela abaya kuhlangabezana ngayo neemfuno zelizwe labasebenzi kunye neemeko zokusebenza kunye nokubonelela ngemilinganiselo yokhuseleko ngokwemisebenzi. | RP | DFFE | Phantsi kweZiphumo 2.3 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokukhutshwa kwekhontrakthi yesibonelelo. |

**Isiphumo 2.4 Umiliselo lwe-ABS kulimo lwaseRooibos luyaqiniswa, luqinisekisa ubulungisa, ubulungisa nozinzo kubudlelwane obufanelekileyo phakathi kwabanini-TK kunye namashishini.**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Umngcipheko** | **Umlinganiselo wokunciphisa** | **Ingcaciso yomsebenzi** | **Amaqumrhu anoxanduva** | **Ingxelo** | **Uhlahlo lwabiwo-mali** | **Ukubaluleka** | **Umhla wokugqitywa** |
| **Umngcipheko 1- Iimpembelelo ezilinganayo ze-ABS kumaqela angahoywanga, kubandakanywa abasetyhini** | Iintlanganiso zokubonisana ngesivumelwano se-ABS kufuneka ziqhutywe ngokwahlukeneyo nabantu baseSan namaKhoi, abantu abantsundu, abasetyhini, ulutsha kunye nabanye abantu abasesichengeni. | Amaqela agxininise nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni ukuze baqonde indima ekuvuneni nasekusetyenzweni kweRooibos, imidla yabo nezinto abazikhethayo kwi-ABS. | RP | DFFE | Phantsi kweZiphumo 2.4 - uhlahlo lwabiwo-mali lweRP | Phezulu | Ukuphela kwexesha lokubonisana |
| **Umngcipheko 2- Umngcipheko wokungonelanga uthethathethwano lwe-ABS** | Isicwangciso sokubonisana nabachaphazelekayo malunga nesivumelwano se-Rooibos ABS. | Imephu yabachaphazelekayo ichonga iqela ngalinye labathathi-nxaxheba ekufuneka kudityanwe nabo kunye nendima yalo ekuvuneni nasekusetyenzweni kweRooibos. Isicwangciso sokubonisana sibandakanya imihla yeentlanganiso, indawo, uluhlu lwabamenyiweyo kunye nee-ajenda. | RP | DFFE | Phantsi kweZiphumo 2.4 - uhlahlo lwabiwo-mali lweRP | Phezulu | Phambi kokuqalisa uthethwano noluntu |
| **Umngcipheko 3- Iinkxalabo okanye izikhalazo eziphakanyiswe ngabachaphazelekayo abathatha inxaxheba kwiingxoxo ze-ABS ezingaqwalaselwanga ngokufanelekileyo.** |  | I-GRM igqityiwe kwaye iyasebenza, kubandakanywa iifomu ezishicilelweyo zokungeniswa kwezikhalazo ezikhoyo kuluntu ngalunye. | DFFE | UNDP | Uhlahlo lwabiwo-mali lwe-SES | Phezulu | Phambi kokwenza imisebenzi yePhulo 2.4 |
| Iprojekthi yeGRM iyasebenza |  | RP | DFFE | Phantsi kweZiphumo 2.4 - uhlahlo lwabiwo-mali lweRP | Phezulu | Ukuphela kwexesha lokubonisana |
| **Umngcipheko 4 - Ukuphathwa kakubi kwelifa lenkcubeko kwiingxoxo ze-ABS** | I-GRM isasazwe kwabo bachaphazelekayo. | Abachaphazelekayo baqeqeshwa kwi-GRM ngexesha leeseshoni zothethwano malunga neefomu ze-ABS eziprintiweyo zokungeniswa kwezikhalazo ezikhoyo kwinqanaba loluntu. | DFFE | UNDP | Phantsi kweZiphumo 2.4 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokugqitywa kwesivumelwano se-ABS |
| **Umngcipheko wesi-5 – Abemi bomthonyama (kuquka amaKhoi namaSan) banokuchaphazeleka kakubi kukuphunyezwa kwemisebenzi, kuquka iMvume yoLwazi yaNgaPhambili yaSimahla (FPIC) engafunyanwanga ngokufanelekileyo.** | ISicwangciso saBantu beMveli (Indigenous Peoples Plan) (IPP) sihlaziywe ukuze siquke iProtocol yeFPIC ukwenzela ukubonisana namaqela amaKhoi kuluntu kwiindawo ekujoliswe kuzo. | n/a | UNDP | n/a | Uhlahlo lwabiwo-mali lwe-SES | Phezulu | Ngaphambi kothethwano kwi-ABS |
| Ukuphunyezwa kwamanyathelo achazwe kwi-IPP | n/a | RP | DFFE | Phantsi kweZiphumo 2.4 - uhlahlo lwabiwo-mali lweRP | Phakathi | Ngaphambi kokugqitywa kwesivumelwano se-ABS |

**Isiphumo 3.1 Inkqubo yoBhaliso lwe-TK edityaniswe nokuhlola izilwanyana nezityalo ezohlukeneyo ixhaswa ukuqinisekisa ukuthotyelwa kwe-ABS kwizivumelwano zangoku nezexesha elizayo phakathi kwabanini bolwazi lwemveli kunye nemveli kunye noshishino**.

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Umngcipheko 1- Umngcipheko wothethwano olunganelanga malunga nenkqubo yobhaliso ye-IKS** | Ukwenziwa kweemephu kunye nesicwangciso sokubonisana nabachaphazelekayo kwiindibano zocweyo zeMithetho yeNkqubo yoLuntu, kubandakanywa ulutsha, abasetyhini kunye namanye amaqela asemngciphekweni. | Ukwenziwa kweemephu kwabachaphazelekayo kuchonga iqela ngalinye labathathi-nxaxheba ekumele kudityanwe nalo, kubandakanywa ulutsha, abasetyhini kunye namanye amaqela asemngciphekweni, kwiindibano zocweyo zeProtocol ye-Bio-cultural Community Protocol kunye nendima yayo Isicwangciso sokubonisana sibandakanya imihla yeentlanganiso, indawo, uluhlu lwabamenyiweyo kunye nee-ajenda. | RP | DFFE | Under Output 3.1 - RP budget | Phezulu | Prior to starting consultations with communities |
| **Umngcipheko 2- Iinkxalabo okanye izikhalazo eziphakanyiswe ngabachaphazelekayo** | I-GRM yeProjekthi iyasebenza  | I-GRM igqityiwe kwaye iyasebenza, kubandakanywa iifomu ezishicilelweyo zokungeniswa kwezikhalazo ezikhoyo kuluntu ngalunye. | DFFE | UNDP | Uhlahlo lwabiwo-mali lwe-SES | Phezulu | Phambi kokwenza imisebenzi yeziphumo 3.1 |
| I-GRM isasazwe kwabo bachaphazelekayo. | Abachaphazelekayo baqeqeshwa kwiGRM ngexesha leeseshoni zokubonisana. | RP | DFFE | Phantsi kweZiphumo 3.1 - uhlahlo lwabiwo-mali lweRP | Phezulu | Ukuphela kwexesha lokubonisana |
| **Risk 3 – Indigenous Peoples (including Khoi and San) may be negatively impacted by the implementation of activities, including Free Prior Informed Consent (FPIC) not properly obtained** | Indigenous Peoples Plan (IPP) updated to include the FPIC Protocol for consultations with Khoi and San groups in communities in the targeted areas for Bio-cultural Community Protocol Workshops and IKS registration system.  | n/a | UNDP | n/a | Uhlahlo lwabiwo-mali lwe-SES | Phezulu | Phambi kocweyo lweProtocol yoLuntu lwezeNkcubeko zeBio |
| Ukuphunyezwa kwamanyathelo achazwe kwi-IPP | n/a | RP | DFFE | Phantsi kweZiphumo 3.1 - uhlahlo lwabiwo-mali lweRP | Phakathi | Phambi kokuqukunjelwa kwenkqubo yobhaliso ye-IKS |
| **Umngcipheko 4 - Ukuphathwa kakubi kwelifa lenkcubeko ngenxa yokulima urhwebo** | **Iprothokholi ekhoyo yokurekhoda nokusebenzisa ulwazi lwemveli kwinkqubo yobhaliso ye-IKS.** | **Ukuphuhliswa kweprothokholi ekurekhodweni nasekusetyenzisweni kolwazi lwemveli kulandela uMthetho woKhuselo, ukuPhakanyiswa, uPhuhliso kunye noLawulo loLwazi lweMveli, wama-2019 kunye neNEMBA (iSahluko sesi-6 kunye neMimiselo ehambelana nayo) kunye nokuqinisekisa ukukhuselwa okupheleleyo kwabo banolwazi lwemveli. Ukongeza, i-IPP iya kubandakanya iProtocol yeFPIC** elandela yemigaqo yokuziphatha nokukhusela Ilifa leNkcubeko eliNgaphathekiyo ze-UNESCO | DFFE | UNDP | Phantsi kweZiphumo 3.1 - uhlahlo lwabiwo-mali lweRP | Phezulu | Phambi kophuhliso lwenkqubo yobhaliso ye-IKS. |

## Ukuphunyezwa kwesicwangciso somsebenzi

Le theyibhile ilandelayo inika isishwankathelo samanyathelo kunye nexesha lokuphunyezwa kwamanyathelo okunciphisa acetywayo.

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Icandelo leProjekthi** | **Iziphumo zeProjekthi** | **Imisebenzi** | * Ngawaphi amanyathelo okunciphisa i-SES?
 | **Igqitywe ngo** | **Umsebenzi ngexesha lokuvezwa kwe-SES** | **Activity when SES package finalized** | **Ngubani?** |
| **Icandelo 1:** Uphando kunye nophuhliso (R&D) lweemveliso ngokuhambelana nenkcazo yokusetyenziswa kwemithombo yofuzo yeNagoya Protocol | **Isiphumo 1.1** Imiqobo ye-R&D edityaniswe nezifundo zeklinikhi kunye nokubhaliswa kweGinger yaseAfrika (Siphonochilus aethiopicus) njengomthombo webhayoloji ukunyanga ukudumba kunye nezifo ezingahambisaniyo nezoyiswayo ngendlela ethobelayo ye-ABS.  | * Ukulungelelanisa isivumelwano se-ABS esiphuhliswe ngokubonisana noluntu oluchongwe kumaphondo aseLimpopo, eMpumalanga naKwaZulu-Natal.
 | * Iintlanganiso zokubonisana ngesivumelwano se-ABS kufuneka ziqhutywe ngokwahlukeneyo nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni.
* Isicwangciso sokubonisana nabachaphazelekayo malunga nesivumelwano se-African Ginger ABS kwiphondo laseLimpopo, eMpumalanga naKwaZulu-Natal.
 | Ukuphela kwexesha lokubonisana | Ö |   | RP |
| * Ukuphuhlisa idossier yexabiso lejinja yase-Afrika ukuze ufumane ilayisensi kwishishini.
 | * Umqulo ocebisa ngexabiso kwijinja yase-Afrika ibandakanya isifundo sokuthotyelwa kwemimiselo yokusingqongileyo kunye namaxwebhu emvelaphi yeGinger yaseAfrika.
 | Ukugqitywa kokuphunyezwa komsebenzi | Ö |   | RP |
| * Umntu onikwe ilayisenisi wazisa iSAHPRA malunga nenjongo yokuthengisa iGinger yaseAfrika ngaphandle kwamabango amayeza
 | * Indlela yokwenza izinto ekhoyo yokubhala nokusebenzisa ulwazi lwemveli lokuhlaziya i-ABS kwiGinger yase-Afrika
 | Ngaphambi kokufumana ilayisenisi |   | Ö | RP |
| Isiphumo 1.2 i-Bioproducting R&D eMntla Koloni iyaxhaswa, ikhulisa uqoqosho lwendawo yokuhlola izilwanyana nezityalo ezohlukeneyo kunye nokuseka ‘Iziko loPhuhliso lweBioproducts’ elibekwe ngobuchule. | * Ukufumana iipemethe eziyimfuneko kunye nezigunyaziso zokusekwa, kweHub
 | * I-ARC ibonisa indlela ezisebenzisa ngayo izitshabalalisi, izichumisi kunye nokusetyenziswa kwamandla kwiziko le-Hub kwiingxelo zabo ze-trimestral.
* I-ARC ibonisa indlela ehlangabezana ngayo neemfuno zelizwe labasebenzi kunye neemeko zokusebenza kwaye ibonelele ngamanyathelo okhuseleko ngokwemisebenzi yokulima kwiingxelo zabo ze-trimestral.
 | Kufuneka igqitywe phambi kokusekwa kweHub. Ixesha elihlaziyiweyo: ingxelo yetrimestra elandelayo kwi-DFFE. | Ö |   | RP |
| * Phuhlisa isicwangciso sophando seminyaka emi-3 seseti ephambili yeentlobo zezilwanyana ezibandakanya iDevil’s Claw kunye noko ubuncinane beentlobo ezincomekayo ezinokulinywa ngokubambisana neDevil’s Claw kwiiprojekthi zoluntu.
 | * Isicwangciso sophando seminyaka emi-3 siquka isifundo sokuthotyelwa kwemimiselo yokusingqongileyo kunye namaxwebhu iDevil’s Claw.
* Iprothokholi ekhoyo yokurekhoda nokusebenzisa ulwazi lwemveli kwisicwangciso sophando iDevil’s Claw.
* ISicwangciso saBantu beMveli (Indigenous Peoples Plan) (IPP) sihlaziywe ukuze siquke iProtocol yeFPIC ukwenzela ukubonisana namaqela amaSan kwiindawo ekujoliswe kuzo.
 | Ukugqitywa kophuhliso lwesicwangciso sophando seminyaka emi-3 | Ö |   | RP |
| * Ukusebenzisa isicwangciso sophando seminyaka emi-3
 | * Ukuphunyezwa kwamanyathelo achazwe kwi-IPP
 | Ukugqitywa kokuphunyezwa kwesicwangciso sophando seminyaka emi-3 |   | Ö | RP |
| * Phuhlisa iindlela zolawulo ezizezona zingcono (BMPs) zokulima nokucwangciswa kokuvuna (iindlela zokuvavanya, ubuchule kunye neendlela) zohlobo ngalunye.
 | * Iintlanganiso zokubonisana ngeDevil’s Claw Best Management Practices (BMP) kunye nenkcazo yeenkonzo zenkxaso kwiiprojekthi zoluntu kufuneka ziqhutywe ngokwahlukeneyo nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni.
* Isicwangciso sokubonisana nabachaphazelekayo malunga nothethwano lweDevil’s Claw malunga neenkonzo zokuxhasa iiprojekthi zoluntu.
 |   | Ö |   | RP |
| * Ukuphuhlisa iindlela zokulawula ezingcono (BMPs) zenkxaso yokulungiswa kwezolimo kunye nokulawulwa komgangatho wokusetyenziswa kwemveliso kuhlobo ngalunye.
 | * Iintlanganiso zokubonisana ngeDevil’s Claw Best Management Practices (BMP) kunye nenkcazo yeenkonzo zenkxaso kwiiprojekthi zoluntu kufuneka ziqhutywe ngokwahlukeneyo nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni.
* Isicwangciso sokubonisana nabachaphazelekayo kudliwano-ndlebe lweDevil’s Claw malunga neenkonzo ezixhasayo kwiiprojekthi zoluntu..
 |   | Ö |   | RP |
| * Ukuseka isicwangciso esilula sokuthengisa, esilinganiselwe ekusekweni kobukho bewebhusayithi efanelekileyo ngenjongo yokuseka unxibelelwano lwemarike.
 | * n/a
 |   | Ö |   | RP |
| * Ukuphuhlisa isicwangciso semveliso enokubakho eMntla Koloni, kunye nezalathi zemveliso
 | * n/a
 |   | Ö |   |   |
| * Yila inkonzo yenkxaso kwiiprojekthi zoluntu apho ii-BMP ezahlukeneyo ziya kudluliselwa rhoqo.
 | * Iintlanganiso zokubonisana ngeDevil’s Claw Best Management Practices (BMP) kunye nenkcazo yeenkonzo zenkxaso kwiiprojekthi zoluntu kufuneka ziqhutywe ngokwahlukeneyo nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni.
* Isicwangciso sokubonisana nabachaphazelekayo malunga nothethwano lweDevil’s Claw malunga neenkonzo zokuxhasa iiprojekthi zoluntu.
 |   | Ö |   | RP |
| * Uluntu luqeqeshelwa izindululo malunga nosetyenziso oluzinzileyo kunye nemilinganiselo yokunciphisa ukusetyenziswa kwezitshabalalisi, izichumisi kunye nokusetyenziswa kwamandla okubandakanyiweyo kwi-BMPs..
 | Ngaphambi kokuba iinkonzo zenkxaso zinikezelwe kwiiprojekthi zoluntu. | Ö |   | RP |
| * Ukubeka iliso kwimveliso
 | * n/a
 |   | Ö |   | RP |
| * Ukuvelisa izithole ezithengiswa/ukunikezelwa kwiiprojekthi zabahlali
 | * I-ARC ibonisa indlela ezisebenzisa ngayo izitshabalalisi, izichumisi kunye nokusetyenziswa kwamandla kwiziko le-Hub kwiingxelo zabo ze-trimestral.
* I-ARC ibonisa indlela ehlangabezana ngayo neemfuno zeemeko zomsebenzi kunye neemeko zokusebenza kwaye ibonelele ngamanyathelo okhuseleko ngokwemisebenzi yokulima kwiingxelo zabo zekota.
 | Kufuneka igqitywe phambi kokusekwa kweHub. Ixesha elihlaziyiweyo: ingxelo yetrimestra elandelayo kwi-DFFE. |   | Ö | RP |
| **Icandelo 2:** Imifuziselo yentsebenziswano ixhasa ulondolozo kunye norhwebo lwezorhwebo kwiimveliso zemveli zebhayoloji | **Isiphumo 2.1** Ukuphunyezwa kwe-Pelargonium Biodiversity Management Plan (BMP) ixhaswa ngentsebenziswano esondeleyo phakathi kweQela eliSebenzayo lePelargonium, amashishini oluntu kunye nabachaphazelekayo kwiCSO. | * Chonga uMphathi weZiphumo
 | * n/a
 |   | Ö |   | RP |
| * Ukuqhuba uvavanyo lolondolozo lwehlabathi/NDF
 | * n/a
 |   | Ö |   | RP |
| * Ukuqhuba uphando lwe-ethnobotanical
 | * n/a
 |   | Ö |   | RP |
| * Ukuqhuba uhlalutyo lwekhonkco lwexabiso kunye nohlalutyo lwentlalo noqoqosho
 | * n/a
 |   | Ö |   | RP |
| * Ukuphonononga kunye nokuhlaziya i-BMP (iphelelwa ngu-2018)
 | * Ukuphuhliswa kweprothokholi ekurekhodweni nasekusetyenzisweni kolwazi lwemveli lwePelargonium, kulandela uMthetho woKhuselo, ukuPhakanyiswa, uPhuhliso kunye noLawulo loLwazi lweMveli, wama-2019 kunye neNEMBA (iSahluko sesi-6 kunye neMimiselo ehambelana nayo) kunye nokuqinisekisa ukukhuselwa ngokupheleleyo kwabo banolwazi lwemveli. Ukongeza, i-IPP iya kubandakanya iProtocol yeFPIC elandela yemigaqo yokuziphatha nokukhusela Ilifa leNkcubeko eliNgaphathekiyo ze-UNESCO
 | Phambi kokuqukunjelwa kweBMP kunye nokuvunywa nguMphathiswa ukuze uluntu luhlomle. | Ö |   | DFFE |
| * Ukuqeqeshwa kwabasebenzi abakhethiweyo abavela kwiDEA, eMpuma Koloni DEDEAT naseFreystata iDESTEA ekuphumezeni iBMP.
 | * Abasetyhini, ulutsha kunye nabanye abantu abasesichengeni baqeqeshelwa ukuvuna endle okuzinzileyo.
 | Ngaphambi koqeqesho kwi-BMP |   |   | RP |
| * Ukuxhasa abanini be-TK ukuba bahlole kwaye baphinde baxoxe ngezivumelwano ze-ABS kunye nezivumelwano zobonelelo
 | * Iintlanganiso zothethwano ngePelargonium Best Management Plan (BMP) kunye ne-ABS kufuneka ziqhutywe ngokwahlukeneyo nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni.
* Ukwenziwa kweemephu kwabachaphazelekayo kuchonga iqela ngalinye labachaphazelekayo ekufanele kudityanwe nalo kunye nendima yalo ekuvuneni nasekusetyenzweni kwePelargonium. Isicwangciso sokubonisana sibandakanya imihla yeentlanganiso, indawo, uluhlu lwabamenyiweyo kunye nee-ajenda.
 | Ukuphela kwexesha lokubonisana | Ö |   | RP |
| * Ukuphuhliswa kwezikhokelo zokuvuna ezizinzileyo
 | * Iintlanganiso zothethwano ngePelargonium Best Management Plan (BMP) kunye ne-ABS kufuneka ziqhutywe ngokwahlukeneyo nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni.
* Ukwenziwa kweemephu kwabachaphazelekayo kuchonga iqela ngalinye labachaphazelekayo ekufanele kudityanwe nalo kunye nendima yalo ekuvuneni nasekusetyenzweni kwePelargonium. Isicwangciso sokubonisana sibandakanya imihla yeentlanganiso, indawo, uluhlu lwabamenyiweyo kunye nee-ajenda.
 | Ukuphela kwexesha lokubonisana | Ö |   | RP |
| * Ukuqeqeshwa kwabaqokeleli bengingqi ukuphucula ukuzinza kweendlela zokuvuna
 | * Abasetyhini, ulutsha kunye nabanye abantu abasesichengeni baqeqeshelwa ukuvuna endle okuzinzileyo.
 | Phambi koqeqesho kwizenzo ezizinzileyo | Ö |   | RP |
| * Ukuququzelela uphuculo lolawulo lweeTrasti ezisekelwe ekuhlaleni, nokusasazwa kweengxowa-mali zetrasti
 | * n/a
 |   | Ö |   | RP |
| * Ukubonelela ngenkxaso-mali kwi-M.Sc. Abafundi
 | * n/a
 |   | Ö |   | RP |
| * Ukuxhasa ulawulo lweQela eliSebenzayo lePelargonium
 | * n/a
 |   | Ö |   | RP |
| **Isiphumo 2.2** Ukuphuhliswa kwendawo yokuvuna iAloe ferox, ukusetyenzwa kunye nokurhweba eMpuma Koloni ukuze kukhuthazwe ukwabelana ngenzuzo okuzinzileyo nokulinganayo kuwo onke amakhonkco exabiso. | * Chonga uMphathi weZiphumo
 | * Abasetyhini, ulutsha kunye nabanye abantu abasesichengeni abaqeqeshwe kulawulo lweProjekthi yoLawulo lweShishini lokuVuna okuZinzileyo
* Ukwenziwa kweemephu kunye nesicwangciso sokubonisana nabachaphazelekayo ukulungiselela ukubandakanya uluntu kwimisebenzi yekhonkco lexabiso leAloe Ferox.
 | Ukuphela kwexesha lokubonisana | Ö |   | RP |
| * Umququzeleli woluntu ozimeleyo
 | * n/a
 |   | Ö |   | RP |
| * Umcebisi woShishino lweAloe
 | * n/a
 |   | Ö |   | RP |
| * Uqeqesho loluntu- Ulawulo lweprojekthi Ulawulo loShishino Uvuno oluZinzileyo
 | * Iintlanganiso zokubonisana malunga nokuvunwa kweAloe ferox, ukusetyenzwa kunye nendawo yorhwebo kufuneka ziqhutywe ngokwahlukeneyo nabasetyhini, ulutsha kunye nabanye abantu abasesichengeni.
* Abasetyhini, ulutsha kunye nabanye abantu abasesichengeni abaqeqeshwe kulawulo lweProjekthi yoLawulo lweShishini lokuVuna okuZinzileyo
 |   | Ö |   | RP |
| * Uluntu luqeqeshelwa izindululo malunga nosetyenziso oluzinzileyo kunye nemilinganiselo yokunciphisa ukusetyenziswa kwezitshabalalisi, izichumisi nokusetyenziswa kwamandla njengenxalenye yolawulo lweProjekthi yoLawulo lweShishini lokuVuna okuZinzileyo.
 | Ngaphambi kokuba iinkonzo zenkxaso zinikezelwe kwiiprojekthi zoluntu. | Ö |   | RP |
| * Ukucwangciswa kwezityalo zokulima endle
 | * n/a
 |   | Ö |   | RP |
| * Ifem yokucebisa ye-EIA ekusekweni kwehektare enye yeAloe kunye neplanti esebenza simahla
 | * n/a
 |   |   |   | RP |
| * Iofisi yeemodyuli esele yenziwe ngaphambili kunye nendibano yocweyo yokulima (kubandakanywa neenkonzo ezininzi kunye nezixhobo zeofisi/ifanitshala)
 | * Umsebenzisi weplanti unikezela ngamaxwebhu kwiRP ukubonisa indlela indawo ezisebenzisa ngayo izitshabalalisi, izichumisi kunye nokusetyenziswa kwamandla. Uhlaziyo lurekhodwa kwiingxelo zekota ukuya kwiRP.
 | Phambi kokuba uqalise ukusebenzisa umzi-mveliso, yonke i-trimestral ingxelo kwi-DFFE emva koko. |   | Ö | RP |
| * Wild harvesting management staff
 | * Bandakanya izabelo zabasetyhini, ulutsha kunye nabanye abantu abasemngciphekweni njengabasebenzi bokuvuna nakwiplanti yokulungisa nokupakisha.
 | Ngaphambi kokuvuna |   | Ö | RP |
| * Kubandakanya ukuthotyelwa kweemfuneko zeemeko zomsebenzi kunye neemeko zokusebenza kwinkqubo yokuthengwa kwezixhobo zabasebenzi nezixhobo zeplanti.
 | Ngaphambi kokuvuna |   | Ö | RP |
| * Umda wokuthengwa kwempahla kufuneka usetyenziswe ekuvuneni endle, ngokunxulumene nabasebenzi bokuvuna, izixhobo kunye nezixhobo.
 | * Bandakanya izabelo zabasetyhini, ulutsha kunye nabanye abantu abasemngciphekweni njengabasebenzi bokuvuna nakwiplanti yokulungisa nokupakisha.
 | Ngaphambi kokuvuna kunye nokusebenza kwesityalo. |   | Ö | RP |
| * Bandakanya ukuthotyelwa kweemfuneko zeemeko zomsebenzi kunye neemeko zokusebenza kwinkqubo yokuthengwa kwezixhobo zabasebenzi kunye nezixhobo zeplanti.
 | Ngaphambi kokuvuna kunye nokusebenza kwesityalo. |   | Ö | RP |
| * Umda wokuthengwa kwempahla kufuneka usetyenziswe ekuvuneni endle, ngokunxulumene nezinto ezityiwayo zabasebenzi bokuvuna kunye nolawulo.
 | * na
 |   |   | Ö | RP |
| * Uvavanyo lweemodyuli ezenziwe kwangaphambili, ukusetyenzwa nokupakishwa (kubandakanya iinkonzo ezininzi kunye nezixhobo zoncedo/ifanitshala)
 | * n/a
 |   |   | Ö | RP |
| * Abasebenzi abavavanyayo, abalungisayo nabapakishayo
 | * I-Operator inikezela ngamaxwebhu kwi-RP (izivumelwano zabasebenzi, iinkqubo zokhuseleko, ubungqina bezinto ezikhuselekileyo njl.) ukubonisa indlela abaza kuhlangabezana ngayo neemfuno zeemeko zomsebenzi kunye neemeko zokusebenza kunye nokubonelela ngemilinganiselo yokhuseleko kwimisebenzi ye-Hub. Uhlaziyo lurekhodwa kwiingxelo zekota ukuya kwiRP.
 | Ngaphambi kokuqala ukusebenza kwesityalo |   | Ö | RP |
| * Ukuthengwa (okanye ukurenta, njengoko kuyimfuneko) kwezixhobo zokusebenza zabasebenzi beplanti
 | * n/a
 |   |   | Ö | RP |
| * Ukuthengwa kwezinto ezisetyenziswayo ukulungiselela abasebenzi nabalawuli
 | * n/a
 |   |   | Ö | RP |
| * Inkampani yokuthengisa
 | * n/a
 |   |   | Ö | RP |
| **Iziphumo 2.3** Amashishini asekwe eluntwini kulimo lweHoneybush ayaxhaswa, eqinisekisa ulondolozo kunye neziphumo zokwabelana ngenzuzo ngokulinganayo kulo lonke elaseCyclopia spp. imbonakalo yomhlaba kwiNgingqi yaseKapa. | * Ukusekwa kweQela leNgxowa-mali leeNgcebiso ngoBugcisa
 | * n/a
 |   |   |   |   |
| * Ukuqhuba uphando olusisiseko lweCandelo le-Honeybush
 | * Uvavanyo lwezibonelelo, isicwangciso sokubeka iliso, iziKhokelo zokuVuna okuZinzileyo, iSicwangciso soLawulo lweBiodiversity siphuhliswa ukwenzela iHoneybush.
 |   | Ö |   |   |
| * Ukuphuhlisa ikhwelo lesibini lesiphakamiso
 | * Iinkalo zenkxaso yezibonelelo ezincinci ezichazwe ngothethwano noluntu ekujoliswe kulo.
 | Ngaphambi kokusungulwa kwefowuni yesibini yesindululo | Ö |   | RP |
| * Ii-NGOs kunye namashishini akhokelwa luluntu kunye namaqela okuvuna endle ayalazi ikhwelo lesindululo, kuqwalaselwa ngokukodwa abafazi kunye namashishini abamnyama.
 | Ngaphambi kokusungulwa kwefowuni yesibini yesindululo | Ö |   | RP |
| *  Imibutho yasekuhlaleni ibonisa indlela imisebenzi ecetywayo elandela ngayo imigaqo yokuvuna ezinzileyo.
 | Ngaphambi kokusungulwa kwefowuni yesibini yesindululo | Ö |   | RP |
| * Imibutho yasekuhlaleni ibonisa indlela eya kuhlangabezana ngayo neemfuno zeemeko zomsebenzi kunye neemeko zokusebenza kwaye ibonelele ngamanyathelo okhuseleko ngokwemisebenzi
 | Ngaphambi kokusungulwa kwefowuni yesibini yesindululo | Ö |   | RP |
| * Iprothokholi ekhoyo yokurekhoda nokusebenzisa ulwazi lwemveli kwiiprojekthi ezixhaswa ngemali yinkxaso-mali encinci yophuhliso lwexabiso le-honeybush.
 | Ngaphambi kokusungulwa kwefowuni yesibini yesindululo | Ö |   | RP |
| * Ukuphonononga izindululo
 | * Izicelo ezingeniswe ngabasetyhini kunye namashishini oluntu abamnyama abekwe phambili.
 | Ngaphambi kokukhutshwa kwekhontrakthi yesibonelelo. |   |   | RP |
| * Ukukhusela ukuvavanywa kweziphakamiso zegranti kwiingozi ezichongiweyo phantsi kwemveliso 2.3 phambi kokuzinikela ngemali.
 | Ngaphambi kokukhutshwa kwekhontrakthi yesibonelelo. | Ö |   | RP ngenkxaso evela kwi-PMU |
| * Izivumelwano zezibonelelo
 | * Uluntu luqeqeshelwa ukuvunwa kwe honeybush ngokuzinzileyo.
 | Ngaphambi kokuphunyezwa kwemisebenzi yezibonelelo |   | Ö | RP |
| * Iigranti zokubeka iliso
 | * Ukuphunyezwa kwamanyathelo achazwe kwi-IPP
 | Ukuphunyezwa kwemisebenzi yegranti |   | Ö | RP |
| * Ukulinganisa ifuthe leNgxowa-mali
 | * N/a
 |   |   |   |   |
| **Isiphumo 2.4** Umiliselo lwe-ABS kulimo lwaseRooibos luyaqiniswa, luqinisekisa ubulungisa, ubulungisa kunye nozinzo kubudlelwane obufanelekileyo phakathi kwabanini-TK kunye noshishino. | * Ukuphanda nokuphuhlisa indlela efanelekileyo yokwabelana ngenzuzo ye-TK ethi ibambe ngokufanelekileyo irenti yomthombo evela kumalungelo e-TK - indlela yokwabelana ngenzuzo elolu hlobo kufuneka isebenze ngokufanelekileyo, ibe selubala, icuthe imingcipheko yorhwebo kwaye yandise inzuzo ye-TK, kwaye iya kufuna umfuziselo wemali nezoqoqosho kwaye uqikelelo;
 | * Iintlanganiso zokubonisana ngesivumelwano se-ABS kufuneka ziqhutywe ngokwahlukeneyo nabantu baseSan namaKhoi, abantu abantsundu, abasetyhini, ulutsha kunye nabanye abantu abasesichengeni.
* Isicwangciso sokubonisana nabachaphazelekayo malunga nesivumelwano seRooibos ABS.
 | Phambi kokuqalisa uthethwano noluntu | Ö |   | RP |
|   | * Ukuphanda nokuphuhlisa iindlela ezingezizo ezemali zokwabelana ngenzuzo ye-TK ezinokuxhasa uluntu olunamalungelo ngokunikela ngeminikelo yesisa nezinye iindlela ezinxulumene noko licandelo labucala.
 | *
 |   | Ö |   | RP |
|   | * Ukuphuhlisa nokuphakamisa ulawulo olufanelekileyo nolulula kunye nenkqubo-sikhokelo yokumisela nokubeka iliso kwindlela yokwabelana ngenzuzo ye-TK.
 | * Ukuphuhliswa kweprothokholi ekurekhodweni nasekusetyenzisweni kolwazi lwemveli lweRooibos, kulandelwa uMthetho woKhuseleko, ukuPhakanyiswa, uPhuhliso noLawulo loLwazi lweMveli, wama-2019 kunye neNEMBA (iSahluko sesi-6 kunye neMigaqo ehambelana nayo) nokuqinisekisa ukukhuselwa ngokupheleleyo kwabo banolwazi lwemveli. Ukongeza, i-IPP iya kubandakanya iProtocol yeFPIC elandela yemigaqo yokuziphatha nokukhusela Ilifa leNkcubeko eliNgaphathekiyo ze-UNESCO
* Ukuphunyezwa kwamanyathelo achazwe kwi-IPP
 | Ngaphambi kokugqitywa kwesivumelwano se-ABS |   | Ö | RP |
|   | * Rekhoda iinkqubo zothethathethwano zangoku ze-SARC njengesifundo somzekelo ngenjongo yokwenziwa “koyilo” lwezinye iimveliso kunye nezivumelwano ze-TK.
 | * n/a
 |   | Ö |   | RP |
|   | * Ukusasaza iziphumo zophononongo njengomzekelo kwabachaphazelekayo be-ABS eMzantsi Afrika nangaphaya
 | * n/a
 |   | Ö  |   | RP |
| **Icandelo 3:**I-Bioprospecting kunye nogqithiso lolwazi olongezelelekileyo luphuculwe kukwabelana ngenzuzo elinganayo | **Isiphumo 3.1** Inkqubo yoBhaliso ye-TK edityaniswe nokuhlola izilwanyana nezityalo ezohlukeneyo ixhaswa ukuze kuqinisekiswe ukuthotyelwa kwe-ABS kwizivumelwano zangoku nezexesha elizayo phakathi kwabanini bolwazi lwemveli kunye nemveli kunye noshishino. | * Iindibano zocweyo kunye namaxwebhu aqukunjelwayo kwiNkqubo yeNkcubeko yoLuntu (i-10 lilonke, iindibano zocweyo ezi-2/ngonyaka)- Iindibano zocweyo kwiPhondo laseMpumalanga
 | * Ukwenziwa kweemephu kunye nesicwangciso sokubonisana nabachaphazelekayo kwiindibano zocweyo zeProtocol yoLuntu lweBio-cultural, kuquka ulutsha, abasetyhini kunye namanye amaqela asemngciphekweni..
 | Phambi kokuqalisa uthethwano noluntu | Ö  |   | RP |
| * Uqeqesho lweSANBI lweerekhoda ze-IK zokuqokelela imizekelo yezityalo – Gxininisa kwizityalo kwiPhondo laseMpumalanga
* Iindleko zeZixhobo zokuRekhoda (incwadi yokubhalela, ikhamera, izincedisi zekhamera, ingxowa yelaptop) ngokwesishicileli se-IK Iiseshoni zoqeqesho kwindlela yoBhaliso
 | * ISicwangciso saBantu beMveli (Indigenous Peoples Plan) (IPP) sihlaziywe ukuze siquke iProtocol yeFPIC ukwenzela uthetha-thethwano namaqela amaKhoi namaSan kwiindawo ekujoliswe kuzo kwiiworkshops zeBio-cultural Community Protocol kunye nenkqubo yobhaliso ye-IKS.
* Ukuphunyezwa kwamanyathelo achazwe kwi-IPP
 | Ngaphambi kokurekhoda |    | Ö  | RP |
| * Ukuphuhliswa kweprothokholi ekurekhodweni nasekusetyenzisweni kolwazi lwemveli olulandela uMthetho woKhuseleko, ukuPhakanyiswa, uPhuhliso noLawulo loLwazi lweMveli, wama-2019 kunye neNEMBA (iSahluko sesi-6 kunye neMigaqo ehambelana nayo) nokuqinisekisa ukukhuselwa ngokupheleleyo kwabo banolwazi lwemveli. Ukongeza, i-IPP iya kubandakanya iProtocol yeFPIC elandela yemigaqo yokuziphatha nokukhusela Ilifa leNkcubeko eliNgaphathekiyo ze-UNESCO
 | Phambi kophuhliso lwenkqubo yobhaliso ye-IKS. | Ö  |   | RP |
| * Iindleko zokubhala i-IK (ababhali abahlanu bebonke)
 | * n/a
 |   |   |   |   |
| * Inkqubo yobhaliso ye-Intanethi ye-IKS iphuhliswe ukuze ibandakanywe kwi-NIKMAS ukuxhasa ukuThotyelwa kwe-ABS
 | * Ukuphuhliswa kweprothokholi ekurekhodweni nasekusetyenzisweni kolwazi lwemveli kulandela uMthetho woKhuselo, ukuPhakanyiswa, uPhuhliso kunye noLawulo loLwazi lweMveli, wama-2019 kunye neNEMBA (iSahluko sesi-6 kunye neMimiselo ehambelana nayo) kunye nokuqinisekisa ukukhuselwa okupheleleyo kwabo banolwazi lwemveli. Ukongeza, i-IPP iya kubandakanya iProtocol yeFPIC elandela yemigaqo yokuziphatha nokukhusela Ilifa leNkcubeko eliNgaphathekiyo ze-UNESCO
 | Phambi kophuhliso lwenkqubo yobhaliso ye-IKS. | Ö  |   | RP |
| **Isiphumo 3.2** Inkqubo yoqinisekiso lwe-biotrade eMzantsi Afrika iphuhlisiwe ngembono yokukhusela ulondolozo lwezityalo nezilwanyana ezohlukeneyo phakathi kwamakhonkco exabiso okuhlola izilwanyana nezityalo ezohlukeneyo. | * Iileta zokuzibophelela
* Isicwangciso sokuPhunyezwa kweTyala lokuGqibela
* Uvavanyo lovavanyo lomngcipheko kunye nezicwangciso zokwenza
* Ingxelo yenkqubela phambili yokuphunyezwa kwesicwangciso setyala
* Ingxelo yeNgxelo yoVavanyo
* UMqulu wokuGqibela weSizwe weBiotrade
* Incwadi yokuGqibela yokuSebenza yeTshatha yeBiotrade
 | * n/a
 |   |   |   |   |
| **Icandelo 4:** Ulawulo loLwazi kunye neM&E. | **Isiphumo 4.0** abachaphazelekayo kuzwelonke nakwamanye amazwe baxhaswa ukuba bathathe inxaxheba kwi-M&E nokucwangcisa izifundo ezifunyenweyo ekuphunyezweni kwayo. | * Abathathi-nxaxheba kuzwelonke nakumazwe ngamazwe baxhaswa ukuba bathathe inxaxheba kwi-M&E nokucwangcisa izifundo ezifunyenweyo ekuphunyezweni kwayo.
 | * n/a
 |   |   |   |  |

# Uphuhliso lwezakhono noqeqesho

## Amalungiselelo eziko

Eli candelo lijolise kuphuhliso lwezakhono kunye noqeqesho olufunekayo ukuqinisekisa ukuphunyezwa okusebenzayo kwe-ESMP. ISebe lezamaHlathi, ukuLoba, kunye nokusiNgqongileyo (DFFE), njengelona qumrhu liphumezayo, kunye namaQela aLawulwayo achongiweyo (RPs) anoxanduva oluphambili lokuphumeza umlinganiselo wokunciphisa, ukuqinisekisa ukubekwa esweni kokuthotyelwa kwale milinganiselo kunye nokunika ingxelo ngokuphunyezwa kwawo..

* **Ukuphunyezwa kunye nokubeka iliso kumanyathelo okunciphisa**

I-PMU kunye nee-RPs ziya kufumana uqeqesho olulungiselelweyo ekuphumezeni nasekulandeleni imilinganiselo yokunciphisa njengoko ibekiwe kwisicwangciso sokubeka iliso kunye nokuphunyezwa kwesicwangciso senyathelo kwiCandelo lesi-2. Oku kuya kuqinisekisa ukuba imilinganiselo yokunciphisa ayiphunyezwanga ngokufanelekileyo nje kuphela kodwa ikwabekelwa iliso ngokuqhubekayo ukuze kuvavanywe ukusebenza kwayo kwaye yenza uhlengahlengiso njengoko kufuneka.

* **Indlela yokunika ingxelo**

Iiprothokholi ezicacileyo zisekwe kwisicwangciso sokubeka iliso kwiCandelo lesi-2 ukuququzelela unxibelelwano olungagungqiyo kunye noxanduva lokuphendula. Amaqela aXophekileyo aya kungenisa iingxelo zenkqubela kwi-DFFE kwi-trimester, echaza ubume bamanyathelo okunciphisa kunye nayo nayiphi na imiba evelayo. Ngapha koko, i-DFFE iya kuqulunqa ezi ngxelo kwaye ibonelele ngohlaziyo oludityanisiweyo kwi-Ofisi yeLizwe ye-UNDP (CO) kwi-trimester. Le ngxelo icwangcisiweyo iqinisekisa ukuchongwa kwemingeni kwangexesha kunye nonxibelelwano oluselubala phakathi kwabo bonke abachaphazelekayo.

* **Uxanduva loqeqesho**

I-UNDP iza kudlala indima ebalulekileyo ekwakheni amandla okuqala e-DFFE kunye nee-RPs, iqinisekisa ukuba banolwazi nezakhono eziyimfuneko ukuze kuphunyezwe ngempumelelo i-ESMP. Ukulandela oku, i-DFFE iya kuthwala uxanduva lokubonelela ngoqeqesho oluqhubekayo nolwethutyana kwiiRPs kubomi bonke beprojekthi. I-UNDP iya kuqhubeka inika inkxaso xa ifuneka, iqinisekisa ukuba izikhewu zezakhono zisonjululwa ngokukhawuleza kwaye uqeqesho luhlala lusabela kwiimfuno zeprojekthi eziphuhlayo. Le ndlela iphindaphindwayo yophuhliso lwezakhono iqinisekisa ukufunda okuqhubekayo, ukuziqhelanisa, kunye nokunikezelwa ngempumelelo kokhuseleko lwendalo esingqongileyo nentlalo kulo lonke iprojekthi.

## Uphuhliso lwezakhono

ISebe lezamaHlathi, ukuLoba, kunye nokusiNgqongileyo (DFFE), njengelona qumrhu liphumezayo, kunye namaQela aLawulwayo atyunjiweyo (RPs) kwisiphumo seprojekthi nganye, baya kufumana uqeqesho olubanzi ukomeleza ukuqonda kwabo kunye nokukwazi ukulawula imingcipheko yokusingqongileyo nentlalontle. . Uqeqesho luya kuqukumbela amacandelo abalulekileyo, aquka uVavanyo lweMpembelelo yokusiNgqongileyo kunye neNtlalo (ESIA), i-ESMP kunye nezicwangciso ezinxulumene nayo, iNdlela yokuLungisa iziKhalazo (GRM), kunye neenkqubo zokubandakanyeka kwabachaphazelekayo.

# Indlela yokulungisa izikhalazo

Jonga uxwebhu olwahlukileyo kwi-GRM

# Uthethathethwano nabachaphazelekayo

Uthethwano nabachaphazelekayo nge-ESMP luya kuqhutywa ngokuhambelana neSicwangciso sokuBandakanya kwabachaphazelekayo ukuqinisekisa intatho-nxaxheba enentsingiselo kunye nobandakanyo. Olu thethwano luya kusebenza njengeqonga labathathi-nxaxheba ukuba baphonononge i-ESMP, baqinisekise imingcipheko echongiweyo, kwaye banike ingxelo ngemilinganiselo yokunciphisa ecetywayo kwisiphumo seprojekthi nganye. Le nkqubo iza kwenza kube lula ukwenza izinto elubala, ubunini, kunye nokuthembana phakathi kwabachaphazelekayo. Ingxelo neengcebiso eziqokelelweyo ngexesha lothethwano ziya kubhalwa ngononophelo kwaye ziqwalaselwe njengenxalenye yexesha lokubhengezwa koluntu lwe-ESMP. Eli galelo liza kudityaniswa kushicilelo lokugqibela lwe-ESMP, liqinisekisa ukuba liyasabela kwiinkxalabo zabathathi-nxaxheba kunye nokubonakalisa izinto eziyinyaniso ezisemhlabeni. Ngokubandakanya ulwazi lwabathathi-nxaxheba, i-ESMP iza komelezwa, iphucule ukusebenza kolawulo lomngcipheko kunye nezicwangciso eziliqili zokunciphisa umjikelo wobomi beprojekthi.