## KNP 3 Yr Plan
KRUGER NATIONAL PARK
INFRASTRUCTURE PROJECT IMPLEMENTATION PLAN 2022/23 -2025-26
INFRASTRUCTURE PROGRAMME - IP4
Item | Region | Rest Camp | Description
1 | Nxanatseni | Olifants | Completion of Unit 9
2 | Marula | Napi | Refurbishment of trails camp
3 | Nxanatseni | Mopani | Renovation of Admin officer's house
4 | Nxanatseni | Mopani | Upgrade of Duty manager's house
5 | Nxanatseni | Shimuweni | Renovation of HSM House
6 | Nxanatseni | Phalaborwa | Renovation of Staff Houses
7 | Marula | Malelane | Upgrade of senior guide house
8 | Marula | Biyamiti | Upgrade of HSM house
9 | Marula | Skukuza | Completion of an old Gym to staff accommodation
10 | Nxanatseni | Sirheni | Renovation of Admin officer's house
11 | Nxanatseni | Sirheni | Upgrade of Duty manager's house
12 | Marula | Skukuza | Replacement of laundry machines and equipment
13 | Marula | Skukuza | Replacement of water pipe line - Huhla
14 | Marula | Tshokwane | New water softener
15 | Nxanatseni | Mopani | New water softener
16 | Nxanatseni | Balalule | Upgrading of the fence- WW
18 | KNP | All Camps | KNP Pavement Management System
Sub-Total
INFRASTRUCTURE PROGRAMME - IP5
Item | Region | Rest Camp | Description
19 | Nxanatseni | Punda Maria | Completion of 2 x 2 Bedroom house
20 | Nxanatseni | Punda Maria | Completion of 2 x 1 Bedroom unit
21 | Nxanatseni | Punda Maria | Renovation of 2 x 1bedroom unit
22 | Nxanatseni | Punda Maria | Renovation of staff Ablution
23 | Nxanatseni | Vlakteplaas | Completion of staff accommodation
24 | Nxanatseni | Shingwedzi | Completion of staff accommodation
25 | Nxanatseni | Woodlands | Completion of staff accommodation
26 | Nxanatseni | Letaba | Completion of staff accommodation
27 | Nxanatseni | Olifants | Conversion of 2-single rooms into 2 x 1-bedroom apartment.
28 | Marula | Skukuza | Renovation of Dingler House
INFRASTRUCTURE PROGRAMME - IP6 YR 1 (CARRY OVER)
Item | Region | Rest Camp | Description
29 | Nxantseni | Letaba | 3 x Tourism Tents 2 bed Replace complete
30 | Nxantseni | Letaba | Living quarters:Upgrade 4 single rooms into 4 x 1 bedroom (Type CC)
31 | Nxantseni | Shingwedzi | Upgrade of Main building Phase 1
32 | Marula | Satara | Tourism units A - Circle unit :13 - 22 : Upgrade
33 | Marula | Satara | Living quarters:Upgrade 6 single rooms into 6 x 1 bedroom (Type CC)
34 | Nxantseni | Olifants | Bungalow Unit NG2U:88 - 105 ( 17 ) :Upgrade Phase 1
35 | Nxantseni | Olifants | Living quarters:Upgrade 4 single rooms into 4 x 1 bedroom (Type CC)
36 | Marula | Bergen dal | Living quarters:Upgrade 8 single rooms into 8 x 1bedroom (Type CC)
37 | Marula | Pretoriouskop | Living quarters:Upgrade 6 single rooms into 6 x 1- bedroom (Type CC)
38 | Nxantseni | Punda Maria | Upgrade of 3 luxury tents
39 | Nxantseni | Sweni | Reconstruction of Trails Camp
40 | Nxantseni | Sweni | Reconstruction camp :Civil services
INFRASTRUCTURE PROGRAMME IP6 YR 2 ALLOCATION
Item | Region | Rest Camp | Description
41 | Nxanatseni | Punda Maria | Upgrade of 4 luxury tents Phase 2
42 | Nxanatseni | Shingwedzi | Upgrade of main building Phase 2
43 | Nxanatseni | Shimuwini | Renovating of 6 Guest Cottage
45 | Nxanatseni | Olifants | Upgrading of bungalow Phase 2 (Unit No 88-105)
47 | Marula | Satara | Renovating of bungalow E circle and G circle
48 | Marula | Tamboti | Refurbishment of 16 existing tents
49 | Marula | Skukuza | Renovation of 3 river view bungalows
50 | Marula | Lower Sabie | Construction of new universal access tent
51 | Marula | Crocodile Bridge | Refurbishment of existing tent
52 | Marula | Crocodile Bridge | Upgrading of bungalows
53 | Marula | Biyamiti | Renovation of guest cottage
54 | Marula | Biyamiti | Renovation of guest cottage
55 | KNP | Sirheni Bateleur Shimuweni | Supply and installation of storage containers in various camp
56 | Marula | Berg en Dal | Renovation of family cottage
57 | Marula | Berg en Dal | Renovation of guest house
58 | Marula | Pretoriuskop | Renovation of existing huts
59 | Marula | Berg en Dal | Demolishing of 8-existing single units and Contruction of 8x 1-bedroom apartment
60 | Marula | Pretoriouskop | Demolishing of 6-existing single units and Contruction of 6x 1-bedroom apartment
61 | Marula | Phabeni | Demolishing of 3-existing single units and Contruct 4x 1-bedroom apartment
62 | Marula | Skukuza | Conversion of dormitories
63 | Nxanatseni | Olifants | Conversion of dormitories into 1 bedroom apartment
64 | Marula | Phabeni to Pretoriuskop | Upgrade of water pipe line
65 | Marula | Skukuza GPP | WPS upgrade of water plant
66 | Marula | Shingwedzi | Upgrade of water plant and fire system
67 | Nxanatseni | Punda Maria | Upgrade of sewer system and water reticulation
68 | Marula | Skukuza | Fire reticulation system upgrading
69 | Marula | Berg en Dal | Replacement of MV Switchgear
70 | Marula | Skukuza | Upgrade and replacing of LT reticulation
71 | Marula | Skukuza | Upgrade and replacing of MV equipment
72 | Marula | Skukuza | Supply and Install new lighting
73 | Nxanatseni | Variuous Camps | Upgrade and replacing of LT reticulation
74 | Nxanatseni | Variuous Camps | Upgrade and replacing of MV equipment
75 | Marula | Skukuza | Refurbishment of exisitng and install new laundry machine
76 | Marula | Nwanetsi | Supply and Install new Solar Hybrid Systems.
77 | Nxanatseni | Vlaakteplaas | Supply and Install new Solar Hybrid Systems.
78 | KNP | Variuous Camps | Supply and install new and retrofit of Solar water heating
79 | Nxanatseni | Punda Maria | Supply and install new Standy hybrid generator power system.
80 | KNP | Variuous Camps | Upgrading of Solar Hybrid and Power systems
81 | KNP | KNP | Upgrade and install new repeater and microwave systems
82 | Marula | Skukuza | Repair of Finance Building Roof
83 | Marula | Skukuza | Repair of TS Building Roof
INFRASTRUCTURE PROGRAMME - IP6 ADDITIONAL
Item | Region | Rest Camp | Description
84 | Nxantseni | Shingwedzi | Upgrade of main building Phase 2
85 | Nxantseni | Mopani | Conference centre deck :Upgrade
86 | Nxantseni | Olifants | Nshawu Guest House (GNG)
87 | Nxantseni | Olifants | Upgrade of trails camp
88 | Marula | Satara | Upgrade of main building
89 | Marula | Skukuza | Upgrade of Bungalows no 97 to 216
90 | Marula | Numbi Gate | Upgrade of gate and reception
91 | Marula | Crocodile Bridge | Replace 12 x tents into 12 x 1bedroom units
92 | Marula | Malelane Gate | Replace 13 x tents into 13 x 1bedroom units
93 | Marula | Malelane Satallite Camp | Replace 2 x Delapidated units into 4 x 1bedroom units
94 | Marula | Numbi Gate | Replace 10 x tents into 10 x 1bedroom units
95 | Marula | Phabeni Gate | Replace 12 x tents into 12 x 1bedroom units
96 | Marula | Kruger Gate | Upgrade of 12 x singlerooms into 12 x 1bedroom units
97 | Marula | Skukuza | Upgrade of 10 x singlerooms into 10 x 1bedroom units
98 | Marula | Skukuza | Conversion of 2 half dormitorie into 2 x 2 bedroom units
99 | Marula | Skukuza | Conversion of Ablution into 2bedroom house at Block D
100 | Marula | Skukuza | Replace 4 park homes into 4 x 1bedroom units at Tubelisha
101 | Marula | Skukuza | Replacement of 2 Asbestos houses into 5 x 2bedroom house at Hippo Circle
102 | Marula | Skukuza | Replace Asbestos house into 4 x 1bedroom unit
103 | Marula | Orpen Gate | Replace 4 x tents into 4 x 1bedroom units
104 | Marula | Phalaborwa Gate | Replace 6 x tents into 6 x 1bedroom units
105 | Nxantseni | Punda Maria | Replace of 10 x tents into 10x 1bedroom units
106 | Nxantseni | Pafuri Gate | Replace of 2 x tents into 4x 1bedroom units
107 | Marula | Skukuza | Upgrade Skukuza soccer stadium
108 | Marula | Malelane Ranger | Renavation of 3 houses and Ablution
109 | Nxanatseni | Shangoni | Shangoni gate development
110 | Nxanatseni | Phalaborwa Hub | New Phalaborwa activity hup phase 1 backers lodge
111 | Nxanatseni | Phalaborwa Hub | New Phalaborwa activity hup phase 1 Hub area
112 | Nxanatseni | Phalaborwa Hub | New Phalaborwa activity hup phase 1 cool down area
113 | Nxanatseni | Phalaborwa Hub | New Phalaborwa activity hup phase 1 public area
114 | Nxanatseni | Phalaborwa Hub | Bulk services
DFFE EPIP BIODIVERSITY INFRASTRUCTURE - TOURISM INFRASTRUCTURE
Item | Region | Rest Camp | Description
153 | Nxanatseni | Punda Maria | Renovation of Tourism Unit
154 | Nxanatseni | Punda Gate | Upgrading of Entrance Gates
155 | Nxanatseni | Letaba | Renovation of Tourism Units
156 | Marula | Satara | Upgrading of Bungalows A Circle
157 | Marula | Satara | Upgrading of Bungalows A Circle
158 | Marula | Orpen gate | Upgrading of Entrance Gates
159 | Marula | Skukuza | Upgrading Wild Fig Guest House
160 | Marula | Skukuza | Renovation of Nyathi Guest House
161 | Marula | Skukuza | Upgrading of Bungalows
162 | Marula | Bergendal | Upgrading of Family Cottage
163 | KNP | KNP | 24 TEAMS INFRASTRUCTURE MAINTENANCEIN KNP
DFFE EPIP ADDITIONAL BIODIVERSITY INFRASTRUCTURE
Item | Region | Rest Camp | Description
164 | Nxanatseni | Punda Maria | Upgrade of two (2) Guest Cottage
165 | Nxanatseni | Shingwedzi | Upgrade of four (4) Guest Cottage
166 | Nxanatseni | Mopani camp | Upgrade of four (4) Guest Cottage
167 | Nxanatseni | Shimuwini | Renovation of four (6) Tourism units
168 | Nxanatseni | Letaba | Upgrade ten (10) Bungalow
169 | Nxanatseni | Olifants | New Family Cottage
170 | Marula | Satara | Upgrade of ten (10) Bungalow :
171 | Marula | Skukuza | Upgrade of twenty (20) Bungalow :
172 | Marula | Lower Sabie | Upgrade of five (5) Guest Cottage
173 | Marula | Berg en Dal | Upgrade of Ten (10) Guest Cottage
174 | Marula | Skukuza | Upgrade Riverview 14 family cottages
175 | Marula | Pretoriuskop | Upgrade of five (5) Bungalow
176 | Marula | Crocodile Bridge | Upgrade 6 single rooms into 6 x 1bedroom unit with sitting, kitchen, shower and Veranda
177 | Marula | Stolsnek | Upgrade 6 single rooms into 6 x 1bedroom unit with sitting, kitchen, shower and Veranda
178 | Marula | Berg en Dal | Upgrade 8 single rooms into 8 x 1bedroom unit with sitting, kitchen, shower and Veranda
179 | Marula | Pretoriuskop | Upgrade 8 single rooms into 8 x 1bedroom unit with sitting, kitchen, shower and Veranda
180 | Marula | Lower Sabie | Upgrade 6 single rooms into 6 x 1bedroom unit with sitting, kitchen, shower and Veranda
181 | Marula | Skukuza | 10x New 2 bedroom house for IDP Personnel
182 | Marula | Skukuza | Upgrade 8 single rooms into 8 x 1bedroom unit with sitting, kitchen, shower and Veranda
183 | Marula | Satara | Upgrade 8 single rooms into 8 x 1bedroom unit with sitting, kitchen, shower and Veranda
184 | Marula | Letaba | Upgrade 8 single rooms into 8 x 1bedroom unit with sitting, kitchen, shower and Veranda
185 | Nxanatseni | Shingwedzi | Upgrade 8 single rooms into 8 x 1bedroom unit with sitting, kitchen, shower and Veranda
186 | Nxanatseni | Olifants | Upgrade 6 single rooms into 6 x 1bedroom unit with sitting, kitchen, shower and Veranda
187 | Nxanatseni | Mopani | Upgrade 8 single rooms into 8 x 1bedroom unit with sitting, kitchen, shower and Veranda
188 | Marula | Phabeni to Pretoriuskop | Upgrade of water line
189 | Marula | Skukuza corporate | Upgrade of sewer line Skukuza staff village
190 | Marula | KNP | Upgrade of water treatment plants and water storage
191 | Marula | Malelane to Berg en dal | Upgrade of water line
192 | Marula | Skukuza | Upgrade of SCM and Warehouse Building
193 | Marula | Various Camps | 10 x New Cattle grids
194 | KNP | KNP | 21 x EPWP teams for Infrastructure Maintenance
National Department of Tourism
Item | Region | Rest Camp | Description
195 | Nxantseni | Shangoni | Construction of Shangoni Gate
196 | Nxantseni | Phalaborwa | Construction of Wild Life Activity Hub